THE INNER PHYSICS OF OUR MIND

30-Day Launch Operations Plan

March 2026  |  Amazon KDP · YouTube · Digital Assets

Revenue Target: $6,000

# 01  Production Timeline

Final edit through publish in 14 days. Every day past Day 7 without an uploaded manuscript delays ARC lead time and review accumulation before launch.

| DAY | PHASE | TASKS |
| --- | --- | --- |
| 1–3 | Final Production | Complete final manuscript proofread. Export clean PDF + DOCX. Commission/finalize cover design (KDP specs: 2560×1600 ebook; 6×9 print). |
| 4–5 | KDP Setup | Create KDP account. Set up title, ISBN (free KDP ISBN or purchase Bowker). Configure ebook + paperback listings. |
| 6–7 | Metadata & Upload | Write book description (A+ Content). Input keywords x7. Select 2 primary BISAC categories. Upload files. Order proof copy. |
| 8–10 | ARC Campaign | Send to 10–15 targeted ARC readers. Provide PDF + review guidance. Set pub date 14 days out. |
| 11–14 | Audiobook Prep | Set up recording environment. Record Introduction + Ch. 1. Edit audio (Audacity/Adobe). Submit test file to ACX. |
| 15 | LAUNCH DAY | Publish ebook + paperback. Announce across all channels. Upload launch YouTube video. |
| 16–20 | Content Push | Daily short-form clips. 3 YouTube long-form videos. Email funnel active. Request ARC reviews go live. |
| 21–25 | Momentum | Analyze conversion data. Double down on highest-performing content. Run limited-time pricing test. |
| 26–30 | Audiobook + Digital Asset | Complete audiobook recording. Launch bonus PDF/workbook. Pitch 2–3 podcast appearances. |

# 02  KDP Setup Checklist

Account & Title Setup

- Create KDP account at kdp.amazon.com

- Enter title: The Inner Physics of Our Mind

- Enter subtitle (see Metadata section)

- Author name: Troy Michael Scott

- Enable DRM: Yes (ebook)

- Select language: English

Content Upload

- Upload interior file: PDF (print) or DOCX/EPUB (ebook)

- Upload cover: JPG, RGB, 300 DPI minimum

- Preview in KDP previewer — fix all errors before submit

- Request proof copy (print) before approving

Pricing & Royalties

- Ebook price: $4.99 (70% royalty tier, delivery cost minimal)

- Paperback price: $14.99 (aim for ~$4–5 royalty after print cost)

- Enroll ebook in KDP Select for 90 days (unlocks Kindle Unlimited + free day promos)

- Do NOT price ebook below $2.99 — drops to 35% royalty tier

# 03  Metadata & Keyword Strategy

Subtitle (Critical for Search)

Suggested: A Structural Inquiry into Consciousness, Subjective Experience, and the Limits of Materialist Explanation

— OR shorter: Why Science Cannot Explain What It Feels Like to Be You

7 KDP Keywords

- consciousness and the hard problem

- philosophy of mind books

- what is consciousness explained

- subjective experience neuroscience

- materialism idealism consciousness

- qualia and inner experience

- mind body problem philosophy

2 Primary BISAC Categories

- PHILOSOPHY / Mind & Body

- SCIENCE / Life Sciences / Neuroscience

Secondary consideration: BODY, MIND & SPIRIT / Inspiration & Personal Growth — monitor if conversion improves.

Book Description (A+ Content Structure)

Open with the central question. State the structural problem. Name what the book does that others don't. Close with stakes. Keep under 400 words. Use line breaks, not long paragraphs.

# 04  ARC Strategy

Advance Reader Copies generate social proof before launch. Minimum 8–10 reviews on Day 1 materially improves Amazon algorithm placement.

Target Readers

- Philosophy of mind academics or grad students

- Consciousness-adjacent YouTubers / podcasters with engaged audiences

- Readers of Chalmers, Dennett, Kastrup, or McGilchrist

- Prior manuscript readers / colleagues

ARC Execution

- Identify 15 targets by Day 3

- Send personalized outreach with PDF + 3-sentence pitch

- Provide simple review guidance: where to post, what to include

- Set review window: 10 days

- Follow up once on Day 7

- Do not request 5-star reviews — request honest reviews

ARC Tools

- BookFunnel — distribute PDF/EPUB securely (free tier sufficient)

- NetGalley — optional if targeting librarians or professional reviewers

# 05  Audiobook Production Plan (Self-Recorded)

Technical Requirements (ACX/Audible)

- Sample rate: 44.1 kHz, 192 kbps MP3

- Peak levels: -3 dB max; RMS: -18 to -23 dB

- Room tone: -60 dB or below

- Submit 1-minute retail audio sample with opening upload

Recording Setup

- Quiet room (closet with clothes = natural dampening)

- USB condenser mic: Blue Yeti or Audio-Technica AT2020 (if not owned)

- Free software: Audacity (noise reduction, normalization, export)

- Pop filter + mic stand

Production Schedule (Days 14–30)

- Day 14–16: Record Introduction + Chapters 1–3. Edit. Review levels.

- Day 17–22: Record Chapters 4–8. Edit in batches.

- Day 23–27: Record Chapters 9–end. Edit.

- Day 28–30: Final master pass. Submit to ACX.

ACX approval takes 2–4 weeks post-submission. Plan audiobook revenue for mid-April at earliest.

ACX Royalty Options

- Exclusive (7 years): 40% royalty — recommended if self-narrating

- Non-exclusive: 25% royalty, distribute via Findaway Voices also

# 06  YouTube Content Calendar — 30 Days

4 long-form videos (10–20 min). Daily short-form (60–90 sec). All content extracts directly from the manuscript — no new research required.

| WEEK | LONG-FORM VIDEO | SHORT-FORM (Daily) |
| --- | --- | --- |
| Wk 1 | "Why consciousness can't be explained by neuroscience alone" (Launch video) | Clip: What is the hard problem? / Book reveal / Consciousness quote |
| Wk 2 | "The difference between brain activity and subjective experience" | Clip: The zombie thought experiment / First-person vs. third-person / Mary's Room |
| Wk 3 | "Can AI ever be conscious? A structural argument" | Clip: What qualia actually are / AI and experience / Integration theory |
| Wk 4 | "What idealism gets right that materialism ignores" | Clip: Book chapter highlight / Reader questions / Author's core thesis |

Short-Form Extraction Protocol

From each long-form video, extract 5–7 clips. Each clip: single strong claim or thought experiment, no more than 90 seconds, hook in first 3 seconds.

- Post to: YouTube Shorts, Instagram Reels, TikTok

- Caption every clip — 85% of short-form viewed without audio

- Use chapter titles and pull quotes from manuscript as on-screen text

Thumbnail & Title Formula

- Thumbnail: dark background, 2–4 bold words, your face optional

- Title formula: [Claim] + [Implication] — e.g., "Neuroscience Can't Explain Consciousness. Here's Why."

# 07  Email Capture Funnel

Structure

Lead magnet → Landing page → Welcome sequence → Book offer.

Lead Magnet Options (choose one)

- "The 5 Problems Materialism Can't Solve" — 5-page PDF (fastest to produce)

- "Consciousness Glossary" — define 20 key terms from the book

- Chapter 1 as free download

Tools (Free/Low Cost)

- ConvertKit (free up to 1,000 subscribers) — email + landing page

- Canva — PDF design

- Linktree or bio link — aggregates all links in social profiles

Welcome Sequence (5 emails, Days 1–10 post-signup)

- Day 1: Deliver lead magnet. One sentence on who you are.

- Day 3: The central question the book asks. No pitch.

- Day 5: One key argument from the manuscript.

- Day 7: Reader social proof / ARC quote.

- Day 10: Direct book offer with link.

# 08  Digital Asset — Bonus PDF / Workbook

Recommended: "The Consciousness Inquiry Workbook"

5–8 pages. Designed to accompany the book. Positions the book as part of a system, not just a read.

Contents

- 3–5 reflection questions per chapter

- The central thesis stated as a proposition to test

- Space for reader's own argument construction

- Suggested further reading (non-competing titles)

Deployment

- Offer free to email subscribers

- Sell standalone at $5–9 on Gumroad or Patreon

- Include as paperback bonus (direct buyers to URL inside book)

# 09  Pricing Strategy

KDP Select enrollment enables strategic pricing levers unavailable outside the program.

Launch Window Pricing (Days 1–7)

- Ebook: $0.99 (Kindle Countdown Deal or free day) — drives volume and rank

- Print: $14.99 — do not discount print at launch

Post-Launch Standard Pricing

- Ebook: $4.99 (sits below $9.99 impulse threshold, above 70% royalty floor)

- Print: $14.99–$16.99 depending on page count and printing cost

- Audiobook: ACX standard pricing (~$14.95 for members, ~$24.95 retail)

Bundling (Optional)

- Ebook + Workbook PDF: $9.99 via Gumroad

- Position as the "complete system" for readers who want depth

# 10  Revenue Projections — March 2026

Assumptions: 30-day window only. No paid advertising. Organic reach via YouTube + email. KDP Select enrolled. Audiobook revenue shifts to April given ACX approval lag.

| SCENARIO | UNITS (Ebook) | UNITS (Print) | AUDIOBOOK | YT/DIGITAL | TOTAL |
| --- | --- | --- | --- | --- | --- |
| Conservative | 80 × $4.99 = $400 | 30 × $14.99 = $450 | $0 (in prod.) | $150 | ~$1,000 |
| Moderate | 250 × $4.99 = $1,248 | 100 × $14.99 = $1,499 | $500 (ACX) | $750 | ~$4,000 |
| Aggressive | 600 × $4.99 = $2,994 | 200 × $14.99 = $2,998 | $1,000 | $1,500 | ~$8,500+ |

Notes

- Conservative: minimal pre-existing audience, slow review accumulation

- Moderate: 8–10 ARC reviews live at launch, 500–1,000 YouTube subscribers, functional email list

- Aggressive: viral short-form clip (100K+ views), podcast mention, or press pickup

$6,000 target falls in the upper moderate to low aggressive range. Achievable with consistent daily content execution and 10+ reviews at launch.

# 11  Critical Path — Non-Negotiables

These are the five decisions that determine whether the launch hits $4K or $8K.

- Cover quality — the single highest-ROI investment. A weak cover kills discovery.

- Reviews at launch — 10+ on Day 1 vs. 0 is not marginal. It is algorithmic.

- Metadata precision — wrong categories mean invisible placement.

- Day-1 YouTube video — must be live at launch. Drives external traffic to listing.

- Email list — even 200 warm subscribers convert at 5–10x cold traffic.

Execution begins Day 1. No plan survives contact with inaction.

Troy Michael Scott  ·  The Inner Physics of Our Mind  ·  March 2026